## Slide 1
AI Adoption Plan
Network Solutions
Prepared by Neha, Manager of Software Engineering
Sponsor: Shrikant Belan Stakeholders: Sanjay, Sanjeev
July 2026
Notes: Plan endorsed in direction at the AI champions review on 28 July 2026. Goal today: sponsor backing for pilot expansion and visibility ahead of the September funding review.

## Slide 2
Purpose
The problem
No consistent approach to AI-assisted development across Network Solutions
Adoption is ad hoc and usage is untracked
No shared infrastructure that individual teams can build on
The proposal
A phased rollout that starts with tooling the team has built and proven on Clear on Behalf (COB), one of our products, and extends it across Network Solutions repos. Governance is built in from the start, not retrofitted later.
Alignment
Endorsed in direction at the AI champions review, 28 July 2026
Aligned to the AI-native SDLC governance model in Colin Wynd's draft paper (Treasury Services): Network Solutions becomes an early implementation of the org-level framework, not a parallel effort
AI Adoption Plan | Network Solutions | July 2026
2

## Slide 3
Current State
Built by the team, piloted on COB
Feature-delivery skill in Claude Code
AI usage tracking system gating GitHub PR merges
Claude Code PR review skill, packaged for marketplace distribution
Dashboard in build: pre and post AIDLC metrics for a before/after view
AI champions review, 28 July 2026
AIDLC pilot results: 2 of 3 defects delivered first-pass
Controlled with/without comparison demonstrated the framework's value
Mandate to converge with the Treasury Services POC (in production use)
Distribution endorsed via the shared skills repo owned by Maveric Xhang
The gap
No other Network Solutions team has equivalent tooling
Adoption elsewhere is individual and unmeasured
No org-level visibility into AI-assisted work, quality impact, or risk points
What this means
The building blocks exist and are proven on one product
The remaining work is convergence, packaging, and rollout, not invention
AI Adoption Plan | Network Solutions | July 2026
3
Notes: COB is the pilot product, not the owner. Convergence with Treasury Services is mandated by the champions and happens before wider distribution.

## Slide 4
Objectives
1
Give every Network Solutions team access to the baseline AI tooling already proven out on COB
2
Make AI usage visible and measurable at the org level, not just on the COB pilot
3
Keep quality and review standards intact as usage scales, using gating rather than trust-based adoption
4
No parallel bureaucracy: reuse the infrastructure already built instead of building new systems per team
5
Align with the org-level AI governance framework so this work scales beyond Network Solutions
AI Adoption Plan | Network Solutions | July 2026
4

## Slide 5
Phased Rollout
1
Codify, Converge, Package
In progress
2
Pilot Expansion
4-6 weeks
3
Org-Wide Rollout
4-8 weeks after Phase 2
4
Governance and Reporting
Ongoing
Convergence with Treasury Services, merge into the shared skills repo, reusable documented components
1-2 pilot teams install via marketplace, friction tracked, weekly syncs
All Network Solutions repos, onboarding guide, per-team POCs, payments group presentation
Standing usage reporting, pre/post AIDLC dashboard, evidence-pack model, skill metadata governance
AI Adoption Plan | Network Solutions | July 2026
5

## Slide 6
Phase 1 and 2: Converge, Package, Pilot
Phase 1: Codify, Converge, Package (in progress)
Feature-delivery skill and PR-gating usage tracker running on COB as the first product
PR review skill packaged into marketplace format
Convergence with the Treasury Services POC: one agreed approach combining their production learnings with the AIDLC architecture (routing by work type, confidence-gated open questions, context-isolated review agents)
Skills merged into Maveric Xhang's shared skills repo with ownership, versioning, and change review defined
Phase 2: Pilot Expansion (4-6 weeks)
1-2 Network Solutions teams with active repos and willing tech leads
PR review skill and usage tracker installed via the marketplace structure
Adoption friction tracked: setup time, false positives in gating, skill misfires
Weekly sync with pilot teams to capture changes needed before wider rollout
Soft gates (warnings) first; hard gates only after the false-positive rate is low
AI Adoption Plan | Network Solutions | July 2026
6

## Slide 7
Phase 3 and 4: Rollout and Governance
Phase 3: Org-Wide Rollout
Marketplace skill and tracker rolled out to all Network Solutions repos
Lightweight onboarding guide: install steps, what gets tracked, what gates a merge
Point of contact per team for first-line support instead of routing everything through the team
Presentation to the payments group, per the champions' direction, as the step beyond Network Solutions
Phase 4: Governance and Reporting (ongoing)
Standing usage report: adoption rate, PRs gated vs passed, time saved where measurable
Pre/post AIDLC metrics dashboard as the primary evidence view, per repo and aggregated
Quarterly review of what the tracker gates on, adjusted with false-positive/negative data
Evolve toward the evidence-pack model: traceable evidence per AI-assisted change, review attention on exceptions and low scores
Skill metadata per the policy mapping model: owner, version, approval status, allowed use cases, defect history
AI Adoption Plan | Network Solutions | July 2026
7

## Slide 8
Governance: AI Usage Tracking
The gating system is the core of this plan's credibility. Without it, AI adoption is anecdote.
Every PR is tagged with whether AI assistance was used and what type (generation, review, both)
Merge gates enforce the same or stricter review scrutiny on AI-assisted PRs, never less
Aggregated data becomes the evidence base for scaling decisions and leadership reporting, not self-reported adoption
The tracker is also the calibration mechanism the governance framework needs: gate outcomes correlated with production defect escapes, so thresholds are validated against reality rather than asserted
MCP governance: a maintained inventory of MCP servers in use (currently Atlassian for Jira and Confluence), including deployment source, auth model, and write scopes, reviewed before any new server is adopted.
AI Adoption Plan | Network Solutions | July 2026
8
Notes: The calibration point matters: scores and gates that are never validated against production outcomes become compliance theater. The tracker closes that loop.

## Slide 9
Risks and Mitigations
Risk | Mitigation
Teams resist a system built by another team | COB positioned as the pilot product, not the owner; ownership moves to the shared skills repo (owned by Maveric Xhang) with named maintainers once merged
Duplication with the Treasury Services POC undermines both efforts | Convergence is mandated by the AI champions; single approach agreed in Phase 1 before wider distribution
Gating creates PR friction and gets bypassed | Soft gates (warnings) in Phase 2; hard gates only after the false-positive rate is low
No time allocated by other teams to onboard | Explicit sponsor backing (Shrikant, with Sanjay/Sanjeev) before Phase 2 starts, not after
Usage data reveals uneven or low adoption | Report it honestly; uneven adoption is itself useful data for where support is needed
Scores and gates drift into compliance theater | Thresholds tied to production outcome data via the tracker; scores kept explainable in the PR
AI Adoption Plan | Network Solutions | July 2026
9

## Slide 10
Success Metrics and Timeline
Success metrics
Network Solutions repos with the tracker and PR review skill installed
% of PRs tagged with AI usage data across those repos
Reduction in review cycle time on AI-assisted PRs vs baseline
Qualitative feedback from pilot team leads by end of Phase 2
Converged approach agreed with Treasury Services and merged into the shared skills repo by end of Phase 1
September funding review: the pre/post AIDLC dashboard is the headline evidence view.
Timeline
Phase | Duration | Owner
1: Codify, Converge, Package | In progress; convergence within 2-3 weeks | Neha, with Treasury Services counterpart
2: Pilot Expansion | 4-6 weeks | Neha + pilot team leads
3: Org-Wide Rollout | 4-8 weeks after Phase 2 | Neha + team POCs
4: Governance and Reporting | Ongoing | Neha, reporting to Shrikant/Sanjay/Sanjeev
AI Adoption Plan | Network Solutions | July 2026
10

## Slide 11
The Ask
1
Sponsor backing from Shrikant to approach 1-2 pilot teams for Phase 2
2
Support for the convergence sync with Treasury Services and the follow-up presentation to the AI champions
3
Sanjay/Sanjeev visibility into this plan ahead of the September funding review, so the usage tracking data supports continued investment
Proven on COB. Converged with Treasury Services. Scaled across Network Solutions.
Notes: Close on the September connection: the tracking data and pre/post dashboard are direct evidence of the initiative's value. The asks are low-cost: backing, a sync, and visibility.